## Bugs
Id | Title | Sev | Pri | Status | Description | Comment
1 | AddPopUp doesn’t display feed titles sometimes | 2 | 2 | Fixed | When a new feed is added that did not exist in the db, then the title is not populated.
2 | Existing feeds can be added | 2 | 2 | Fixed | When a feed that already exists is added directly, then there is no UI feedback that the feed already existed so was not added. The UI says "feeds added".
3 | Sometimes AddPopUp gives no f/b | 2 | 2 | No Repro | When trying to add partial_atom1.xml, no feed details were displayed.
4 | DaemonServiceTest.TestUndatedCrawl1 fails | 2 | 2 | Fixed | DaemonService should not add the two test undated items as new items. | When I manually add test items to the Feed in PrepareForUndatedTest, I did not set the insertedOn date. I have fixed that by manually setting the insertedOn date to Now.
5 | FeedControllerTest.TestAddPopUpValidSupportedFeed fails | 2 | 2 | Active | When run as a stand-alone test it passes, but fails when run as part of suite. Joel feed has the wrong LastCheckedDate. See associated log file for details.
6 | Unable to add RSS feeds from http://news.google.com/nwshp?client=firefox-a&rls=org.mozilla:en-US:official&hl=en&tab=wn | 1 | 2 | Fixed | There are two link tags - one for the icon and another for the RSS page - one after the other. The regex inside ScanPage is not able to distinguish this and takes the icon href as the potential RSS link.
7 | Modify FeederNaiveBayesModelTest cases to take into account that vocabulary and stopword are always populated | 2 | 2 | Active | Because of the long time it takes to populate vocabulary and stopword with real world data I have changed the textmining_testdata.sql to not modify those tables. This script is used in FeederNaiveBayesModelTest and a couple of tests are failing because of this.
8 | Some items are showing up twice in prod | 2 | 2 | By Design | http://www.nytimes.com/2009/06/14/business/global/14g8.html?_r=1&partner=rss&emc=rss, http://www.nytimes.com/2009/06/14/world/middleeast/14memo.html?partner=rss&emc=rss, http://www.nytimes.com/2009/06/14/sports/golf/14woods.html?partner=rss&emc=rss showed up twice. | All these items had different publish dates. There is no way to catch such duplicates. Only dateless items are checked for duplicates.
9 | Some items are showing up multiple times | 2 | 2 | Active | Item Ids 11544 and 11774 are showing up twice. | These items were inserted in two different runs. They had valid published dates. Item deails added in logs
10 | Google news date format is not recognized causing a bunch of warnings | 2 | 2 | Fixed | Google news (http://news.google.com/news?ned=us&hl=en&topic=h&output=rss) has dates in this format - Tue, 22 Dec 2009 00:28:57 GMT+00:00 which is not recogized by the standard .NET parser or Avilay.Utils parser. | Fixed in Avilay.Utils by adding another special case.
11 | Bunch of items in SeattlePI and other feeds show up as missing dates. | 2 | 2 | Active | Missing item published date for : http://www.seattlepi.com/business/413130_costcocoke10.html?source=rss. Upon checking the RSS, the item does have a pubDate. The code path suggests that it is not related to parsing but the actual element is not discovered.

## Next Tasks
1 | Try to repro economic times bug
2 | Debug self search bug
3 | Fix url exception
4 | Clean user history